## incidentData
CustomerImpacting | Conditions | Priority | HSE# | Street | Town | ST | FMA | Assigned | Event | RegionAbbr | From Pole # | To Pole # | Span # | Cable Footage | Created On | Status | DESC
No | Accessible/other work needs to be done first | LOW |  | Hillside Rd | TOPSHAM | ME | PORTSMOUTH | ICON | GBR - April 10-2020 Noreaster | GBR | 30.1 | 0 | 1 | 200 | 04/10/2020 12:22:07 | CLOSED | 4/10/2020, KBlodg001: Drop only complete *DESC END*
No | Accessible/other work needs to be done first | LOW | 49 | Wood Schoolhouse Road | BOWDOIN | ME | PORTSMOUTH | ICON | GBR - April 10-2020 Noreaster | GBR | 18/4;4 |  |  |  | 04/10/2020 13:18:21 | CLOSED | 4/11/2020, KBlodg001: Transfer complete *DESC END*
No | Accessible/other work needs to be done first | LOW | 1112 | Main Street | BOWDOIN | ME | PORTSMOUTH | ICON | GBR - April 10-2020 Noreaster | GBR | 119;5 |  |  |  | 04/10/2020 13:23:20 | CLOSED | 4/11/2020, KBlodg001: Transfer complete *DESC END*
No | Accessible/other work needs to be done first | LOW |  | Litchfield Rd | BOWDOIN | ME | PORTSMOUTH | ICON | GBR - April 10-2020 Noreaster | GBR | 8 | 0 | 1 | 0 | 04/11/2020 10:05:33 | CLOSED | 4/11/2020, KBlodg001: Transfer complete *DESC END*
No | Accessible/other work needs to be done first | LOW |  | Augusta Rd | TOPSHAM | ME | PORTSMOUTH | ICON | GBR - April 10-2020 Noreaster | GBR | 67 | 0 | 1 | 0 | 04/11/2020 10:06:33 | CLOSED | 4/11/2020, KBlodg001: Transfer complete *DESC END*
No | Accessible/other work needs to be done first | LOW |  | Bullrock Rd | WEST BATH | ME | PORTSMOUTH | ICON | GBR - April 10-2020 Noreaster | GBR | 4 | 0 | 1 | 0 | 04/11/2020 10:07:30 | CLOSED | 4/11/2020, KBlodg001: Transfer complete *DESC END*
No | Accessible/other work needs to be done first | LOW |  | Fernwood rd | WEST BATH | ME | PORTSMOUTH | ICON | GBR - April 10-2020 Noreaster | GBR | 4 | 0 | 1 | 0 | 04/11/2020 10:08:14 | CLOSED | 4/11/2020, KBlodg001: Transfer complete *DESC END*
No | Accessible/other work needs to be done first | LOW |  | Rockweed Rd | WEST BATH | ME | PORTSMOUTH | ICON | GBR - April 10-2020 Noreaster | GBR | 7 | 0 | 01 | 0 | 04/11/2020 10:08:53 | CLOSED | 4/11/2020, KBlodg001: Transfer complete *DESC END*
No | Accessible/work can start immediately | LOW |  | Tracy Ln | TOPSHAM | ME | PORTSMOUTH | ICON | GBR - April 10-2020 Noreaster | GBR | 33 | 3.1 | 1 | 250 | 04/11/2020 12:17:46 | CLOSED | 4/11/2020, KBlodg001: Transfer complete Span back up *DESC END*
No | Accessible/work can start immediately | LOW |  | Royalsborough Rd | DURHAM | ME | PORTSMOUTH | ICON | GBR - April 10-2020 Noreaster | GBR | 180 | 180.1 | 1 | 200 | 04/11/2020 13:57:13 | CLOSED | 4/11/2020, KBlodg001: Very low line blocking lane of traffic
No | Accessible/work can start immediately | LOW |  | Bullrock Rd | WEST BATH | ME | PORTSMOUTH | ICON | GBR - April 10-2020 Noreaster | GBR | 4 | 4.1 4.2 | 3 | 600 | 04/13/2020 09:03:49 | CLOSED | 4/13/2020, KBlodg001: Hook pole only